## Summary
TDS Environment Tracker Tool
Sprint 0 |  | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5
Completed: Visual Studio Software Installation and setup. • Server and Database configuration. |  | Completed: •Login Screen design •Home Screen Design • Allocate New Environment screen design • Navigation between screens and Role based Authorization | Completed: •Data base setup and table creation. • Load environments data to database • Link database to Screens | Completed: • Tabs and dropdown need to add in Home Screen. • Display all the allocated TEST environments by Default when Home screen is displayed. • Display all the unallocated TEST environments when the unallocated option selected in Home screen. • Single Page Functionality. | Completed: • Search and display the records based on database,db2databasey,ndvr parallel,projectowner, and project name. Pending: • Display all the allocated SYS environments when moved to SYS tab in Home screen. (functionality between the tabs and dropdown is not completed.) • Display all the allocated USER environments when moved to USER tab in Home screen. | Completed: •Added the Edit and Delete functionality . • Display the SYS unallocated environments when the Applications seleted on SYS Option. • Display the USER unallocated environments when the Applications seleted on USER Option. Pending: • Charts based on the environments allocated to project in Dashboard.